## Lead Engineer Grooming
SR NO | Issue | Area | Issue Description | Help required from | Solution/Comments / Actions | Image | Issue raised by | Date issue opened | Date issue closed | LL/Q&A/KSS | Status | Links | Lesson Leant published
0 | APQP 3DX Migration | APQP | 3DX APQP work process | Help need from any LE who has staring working on 3DX APQP | 3DX APQP work process not clear, how to work in 3dx APQP, refer sharepoint link for online 3dx. Offline APQP can be found in shared folder to run apqp meeting with supplier in the dowtime. | NA | Nivil Jose | 2025-05-08 | 2025-05-23 | Q&A | Closed | https://outlook.office.com/book/APQP3DXTrainingBooking@jlrglobal.onmicrosoft.com/?ismsaljsauthenabled=true
1 | UBOM Migration | 3DX | VSMs missing with the parts. | Help required from CAD team to identify the parts those are missing in each VSM and to add them appropriately with all the necessary properties filled in. | Pre P release collaboraive task needs to be raised, post P release Iceate has to be raised to update usage according to the VSM/market | NA | Nivil Jose | 2025-05-08 | 2025-05-23 | Q&A | Closed
2 | HET part CAD- missing fixing | CAD | CAD sent for HET25 Maching of spoiler, has no fixing data in them. Physical parts generated for HET25 has no fixings and Build stopped. | Corrective action required from CAD team to prevent future issues | The Missing fixings were provided to the proto maker, fixings arranged from the supplier by LE to sort this issue. Checklist created to avoid such issues. |  | Sandeep Mote | 2025-06-23 | 2025-07-03 | LL | Closed | Checklist created to avoid such issues
3 | Sevice release Parts | Icreate | 1) Do we need specific EIs for service parts 2) If required need CAD data in EIs | From LEs who previously/currently worked on service part release icrt.- Sumit,Anudeep,Arvind | 1) Yes,Specific EIs for service parts are required,which need to nested to main assembly EIs 2) If CAD is in 3DX,then yes CAD need sto be added in EIs. If CAD is in V5- Empty EIs are also Okay. Detail solution added in sr.no 16. | PDF added in Support document folder | Nivil Jose | 2025-07-30 | 2025-09-24 | Q&A | Closed | Link to create a Nested EI structure in 3DEXP Training - UBOM -> UBOM for CAD Author -> Creating a new Assembly EI Final with Child EI Components (Nested EI's) : https://jlrglobal.sharepoint.com/sites/3d-experience-training-online/SitePages/UBOM-for-CAD-Authors.aspx
5 | PIR access | PPIR | 1) How to download PPIR from RADs 2) How to request PIR access for engineer/DBMI approval site | From LEs who previously/currently worked on access for PPIR - LE's Sandeep helped to show how to download once you have access | Linked shared to download PPIR |  | Saddam | 2025-08-05 | 2025-08-05 | Q&A | Closed | PIR link - https://rads.jlrint.com/ppir/ppir.asp
6 | PIR Report Approval | PPIR | 1) How to download, Check and approve the PIR report. | Help need from LEs How to Approve report? Sandeep helped me on How to Approve report in PIR System. | Detail explanation given by LE and query has been resolved. |  | Rahul Phatangare | 2025-08-06 | 2025-08-06 | Q&A | Closed | https://rads.jlrint.com/ppir/ppir.asp
7 | New CA/CO creation Guidance | 3DX | to understand the CA/CO creation process | Rupesh Helped to understand it properly | shared the link for CA/CO creations and explained it on the call how to create it. Refer to sharepoint link. | NA | Sandeep Mote | 2025-08-07 | 2025-08-07 | Q&A | Closed | https://jlrglobal.sharepoint.com/sites/3d-experience-training-online/_layouts/15/stream.aspx?id=%2Fsites%2F3d%2Dexperience%2Dtraining%2Donline%2FShared%20Documents%2FDocumentation%2FP%20Release%20for%20L481%20and%20EMA%2FTactical%20release%20process%2FInitial%20P%20Release%2FMLA%20IR%20Webinar%2Emp4&referrer=StreamWebApp%2EWeb&referrerScenario=AddressBarCopied%2Eview%2E5b9e06ad%2D39a4%2D4008%2Db0ca%2D9ab6d5717ff1
8 | EBER3 Reference required | EBER | wanted the reference for the EBER3 review evidence pack | help needed from L.E for the EBER3 review evidence pack sandeep provided the ref pack | Share the EBER3 reference documnet and explained the details required for it on call. Refer attached EBER's evidence pack in one drive. | NA | Rupesh Nikule | 2025-08-07 | 2025-08-07 | Q&A | Closed
9 | Currency related issue on the Risk ticket | JIRA | help required to understand the impact of different currencies like EURO and GBP | Nivil helped to sort this currency issue | explained on the call how to sort the different currency issue. | NA | Sandeep Mote | 2025-08-06 | 2025-08-06 | Q&A | Closed
9 | Subsequent CAD release | Icreate | Need to help to draft a subsequent Cad release in system with UP Suffix CLI | Need help from LE who has experience in subsequent release | Refer to the tanining link for UP suffix release | NA | Anudeep Mamidi | 2025-08-11 | 2025-08-13 | Q&A | Closed | https://jlrglobal.sharepoint.com/sites/3d-experience-training-online/Shared%20Documents/Forms/tags.aspx?id=%2Fsites%2F3d%2Dexperience%2Dtraining%2Donline%2FShared%20Documents%2FDocumentation%2FIn%20Vehicle%20Software%20%28IVS%29%2FCAD%20%2D%20Subsequent%2FBranching%20%28up%2DCLI%29%20the%20EI%2Epdf&parent=%2Fsites%2F3d%2Dexperience%2Dtraining%2Donline%2FShared%20Documents%2FDocumentation%2FIn%20Vehicle%20Software%20%28IVS%29%2FCAD%20%2D%20Subsequent
10 | Pre-sale RIS | RIS | Need to Rework all pre-build cars. keys are specific to VIN numbers. Need to undserstand 1. If parts are ETS, can parts be directly sent to rework team. 2. Who will be doing the rework on the cars. | Need help from LE who has experience in Rework | International upgrade team will contcat you regarding parts availability ETA, at that time you confirm the delievry address as well. Its good to deliver the parts at rework location. | NA | Gaurav Gupta | 2025-08-11 | 2025-08-13 | Q&A | Closed
11 | 26MY SV Cridix deleted in 80428 icreate | Icreate | The 80428 iCreate executed in which the 26MY part T9XM-8200-AA deleted in redbook. Need to check how we can add it in redbook. | Need help from LE who has experience in iCreate redbook updates | 8/13/2025 : Need to discuss with Admin team how we can update the 26MY part in redbook. LE need to review cridix internally before confirming to admin team at REQUEST phase before GL approval. | N/A | Akash Hanwate | 2025-08-13 | 2025-08-13 | Q&A | Closed | iCreate number 80428 : https://icreate.jlr-ddc.com/propose-change/summary/summary
12 | VSM L384 Core part carryover | GENERAL | we have core valance carryover in SV with new technical paint. ERS asked me that she cannot provide two CCR for one part. so created dummy with same T8U2 part as we are unsure of supplier who it will be | suggestion from experince LEs needed whether anyother way possible | we need separate cost number for carryover parts if supplier is different as it will new supplier will charge handling cost to it. it doest affect EBOM structure and there it will be same number. Cost collector required for hadling cost. | NA | suraj powar | 2025-08-13 | 2025-08-13 | Q&A | Closed
13 | Service release UBOM | RELEASE | Service parts required specific EIs and should be visible in VSM. However, whether it is allowed to keep the same part in production assembly and a separate EI for Service part. Both will be visinble in VSM | ERS, anyone has experience | Sameer- Duplicate parts visible in VSM is OK, that is Service only release will be visible in separate EI and the same part will be visible in Production assembly EI as well. Nivil - For those parts already released for service but has no EI generated, it is necessary to create a new EI to add usage to the current program to use as a service part for the current program. It wont affect the previous release. We can have Same EI number for N number of times, but all will have diffrerent PRD number, so the VSM will use that particular PRD number used for releasing that part. You need to add usage codes or statements other than CCR codes. | NA | Nivil Jose | 2025-08-28 | 2025-09-24 | Q&A | Closed
14 | UBOM Structure | CAD | UBOM training | anyone has experience | Go through taining pack | NA | Sameer Joshi | 2025-08-28 | 2025-09-23 | knowlege sharing | Closed | https://jlrglobal.sharepoint.com/sites/3d-experience-training-online/SitePages/Webinar%20Schedule.aspx?csf=1&e=5BMt4m
15 | DT2 Part rlease and CAD structure | RELEASE | PIA part release(component) DT2 | ERS, anyone has experience | Nivil - Should be under an EI and should be nested in top level EI if the PIA or EI not released in the system, the DT2 part can be added as the PIA to the EI | NA | Saddam Shaik | 2025-08-28 | 2025-09-24 | Q&A | Closed
16 | CA/CO in Icreate | RELEASE | CA/CO for icreate | ERS, anyone has experience | there is a video for training session to create the CA/CO creation process | NA | Sanddep Mote | 2025-08-28 | 2025-09-23 | knowlege sharing | Closed | https://jlrglobal.sharepoint.com/sites/3d-experience-training-online/_layouts/15/stream.aspx?id=%2Fsites%2F3d%2Dexperience%2Dtraining%2Donline%2FShared%20Documents%2FDocumentation%2FP%20Release%20for%20L481%20and%20EMA%2FTactical%20release%20process%2FInitial%20P%20Release%2FMLA%20IR%20Webinar%2Emp4&nav=eyJwbGF5YmFja09wdGlvbnMiOnsic3RhcnRUaW1lSW5TZWNvbmRzIjoxMC4wMjI3OTd9fQ%3D%3D&referrer=StreamWebApp%2EWeb&referrerScenario=AddressBarCopied%2Eview%2Ebcf6b74f%2D258b%2D435a%2Dbb11%2Db62e5ece4088
17 | Orange Peel issue resolution | WCPA | Orange peel issue on body painted RH side D Post finisher | anyone has experience | Parts were checked if molded correctly. Paint build up thickness analysis was done to measure coating thickness and found that thickness of Primer & basecoat was less compare to LH (LH was found Ok) Robotic paint program was set differently for LH & RH side D Post finisher. Hence paint program optimised for Orange Peel (minor reduction of BASE/BC viscosity) for LH D post finisher and increased the paint thickness as per layers to overcome orange peel issue. | NA | Sagar Gagare | 2025-05-12 | 2025-07-21 | LL | Closed
18 | DT, GRADE, EMC | GENERAL | Brand new/Re-useDT, GRADE, EMC for actuators and connectors | Anyone with experience on GRADE, EMC & DT | Arvind & Nivil - ECAS to be raised for New and Reuse GRADE & EMC. A training to be completed to get the access to ECAS. DT require access EAC application to be installed or run on the system. ECAS link shared | NA | Arvind Udgi | 2025-08-28 | 2025-12-16 | knowlege sharing | Closed | ECAS access and training is hosted here; https://jlrglobal.sharepoint.com/sites/electronicslessons/SitePages/ECAS-Webinars.aspx
19 | AAR Deviation | AAR | Deviation raised for AAR approval prior to the off tool parts | anyone has experience | Need to fill up the JLR Perceived Quality Cosmetic Deviation Form. Will have more information by next week once AAR team is back. Devaition need to raised againt the requirement in S-dots | NA | Swapnil Dalvi | 2025-09-12 | 2025-11-18 | Q&A | Closed | https://jlrglobal.sharepoint.com/:p:/r/sites/MLA27MYMCFSV-EXTERIORS_GRP/_layouts/15/Doc.aspx?sourcedoc=%7B7949E75C-8787-41D5-9AEE-55995AF052D0%7D&file=20251010_L460%2028MY%20SV%20Radiator%20Grille%20Stress%20Mark%20Deviation.pptx&action=edit&mobileredirect=true https://jlrglobal.sharepoint.com/sites/MLA27MYMCFSV-EXTERIORS_GRP/Shared%20Documents/Forms/AllItems.aspx?viewid=5fa9a06f%2D09e5%2D4ae2%2D994e%2D176c761c998d&csf=1&web=1&e=qeuRLr&FolderCTID=0x012000F46C83D4C1DFE148AEB509A111C1BFFD&id=%2Fsites%2FMLA27MYMCFSV%2DEXTERIORS%5FGRP%2FShared%20Documents%2FGeneral%2FL460%20%2D27MY%2F07%2E%20OQ%2DPQ%2FL460%2028MY%20SV%20Radiator%20Grille%2FDeviation%2FSTJLR%2E01%2E5019%2Epdf&parent=%2Fsites%2FMLA27MYMCFSV%2DEXTERIORS%5FGRP%2FShared%20Documents%2FGeneral%2FL460%20%2D27MY%2F07%2E%20OQ%2DPQ%2FL460%2028MY%20SV%20Radiator%20Grille%2FDeviation |  |  | Q2 | Q3 | Q4
20 | How to raise PR AIMS | AIMS | Need help to raise PRAIMS against ongoing build issue, for which we are requesting design change to supplier | anyone has experience | AIMS 2, PR AIMS. PR AIMS can be raised in AIMS3 JIRA, SME will manage the PR AIMS. | NA | Sanket Kotkar | 2025-09-12 | 2025-11-05 | Q&A | Closed | I have come across below link for the PRAIMS. Please check if it helps : 1)JLR-HTG-557086 Creation of Robust PR-AIMS with Quality Content : https://jlrglobal.sharepoint.com/sites/jlrway/en-gb/wi/Pages/Creation-of-Robust-PRAIMS-with-Quality-Content-1603726713284.aspx 2) JLR-HTG-557086 Creation of Robust PR-AIMS with Quality Content : https://jlrglobal.sharepoint.com/sites/jlrway/en-gb/procedures/Pages/dlloyd13_automated_issue_management_aim_-_prevent_recurrence_.aspx#/related-content |  | LL | 2 | 0 | 0
21 | Understand the PCDS process | GENERAL | Need a brief intro on the PCDS process | anyone has experience |  | NA | Shilajit Pal | 2025-10-07 | 2025-10-19 | Q&A | Closed | https://hrselfservice.jlrint.com/hr_direct/cgi-bin/pcr000af.cgi |  | Q&A | 14 | 18 | 3
22 | PCAR access DC7 | GENERAL | Access required for entering the build/production plant | anyone has experience | PCAR link added. Site currently down due to system outage issue. | NA | Sanket Kotkar | 2025-10-08 | 2025-10-19 | Q&A | Closed | https://hrselfservice.jlrint.com/hr_direct/cgi-bin/pcr000af.cgi |  | KSS | 2 | 4 | 8
23 | PCAR access Gaydon | GENERAL | Access required for entering the Gaydon premises | anyone has experience | PCAR link added. Site currently down due to system outage issue. | NA | Sanket Kotkar | 2025-10-08 | 2025-10-19 | Q&A | Closed | https://hrselfservice.jlrint.com/hr_direct/cgi-bin/pcr000af.cgi
24 | PCAR access Solihul | GENERAL | Access required for entering the build/production plant | anyone has experience | PCAR link added. Site currently down due to system outage issue. | NA | Sanket Kotkar | 2025-10-08 | 2025-10-19 | Q&A | Closed | https://hrselfservice.jlrint.com/hr_direct/cgi-bin/pcr000af.cgi
25 | PCAR access Halewood | GENERAL | Access required for entering the build/production plant | anyone has experience | PCAR link added. Site currently down due to system outage issue. | NA | Sanket Kotkar | 2025-10-08 | 2025-10-19 | Q&A | Closed | https://hrselfservice.jlrint.com/hr_direct/cgi-bin/pcr000af.cgi
26 | WCPA area | GENERAL | Access required for entering WCPA | anyone has experience | PCAR link added. Site currently down due to system outage issue. | NA | Sanket Kotkar | 2025-10-08 | 2025-10-19 | Q&A | Closed | https://hrselfservice.jlrint.com/hr_direct/cgi-bin/pcr000af.cgi
27 | Dress code in plant/hivis/safetyshoes | GENERAL | Plant Ethics | anyone has experience | Safety shoes, watch/belt covers required in assembly zones. Jeans not allowed in DC7 plant. High Vis required only in stores and not required for assembly zones. DC7 induction ppt link to be added | NA | Sanket Kotkar | 2025-10-08 | 2025-10-19 | Q&A | Closed | PPT added on share folder
28 | VEPS requirement | VEPS | VEPS requirements for each gateway | anyone has experience | KSS arranged with wider team and links added | NA | Arvind Udgi | 2025-10-08 | 2025-10-19 | knowlege sharing | Closed | https://jlrglobal.sharepoint.com/sites/veps/Shared%20Documents/Forms/AllItems.aspx?csf=1&web=1&e=7yuhNN&CID=f611b62c%2D9ffa%2D4ba0%2Da7b7%2Dd9cfbd1bcfb4&FolderCTID=0x01200002B3E001137568418B8A2B302F89CC7F&id=%2Fsites%2Fveps%2FShared%20Documents%2F01%2E%20VEPS%20SCHEDULES%2FTOP%20HAT%2FBES
29 | PPD(painted parts) | GENERAL | Paint process sheet including paint application process/parameters | anyone has experience | PPD contains all the information about paint application including different layers of paint, thickness, curing and other process parameters | NA | Sagar Gagare | 2025-10-08 | 2025-10-15 | knowlege sharing | Closed | https://jlrglobal.sharepoint.com/:x:/r/sites/L663SV27MYEU7EmissionsUpdate_GRP2/Shared%20Documents/General/05%20Engineering/Sagar/L663%2026MY%20SV%20OCTA%20%26%20MCF/PPD/Minth/EDP-PPD.XLSX?d=w5d94a37ce9e241fbad213405993712f0&csf=1&web=1&e=YCw3qS
30 | ALERT in Jira | ALERT | New ALERT process in Jira | anyone has experience | Work around inplace for WERS alert after IT issue | NA | Sumit | 2025-10-20 | 2025-10-20 | Q&A | Closed | added in Share folder
31 | Collaborative task | 3DX | Adding newly created EI parts in VSM without Icreate | anyone has experience | Training link added | NA | Arvind Udgi | 2025-10-20 | 2025-12-26 | Q&A | Closed | EBOM change request during virtual series.mp4
32 | OKTUL for Usage matrix | GENERAL | How to refer the Usage matrix | anyone has experience | Tableau link shared | NA | Arvind Udgi | 2025-10-20 | 2025-12-22 | Q&A | Closed | https://jlrglobal.sharepoint.com/sites/tableau
33 | Fastner OKTUL | GENERAL | How to refer to the Fastner library | anyone has experience | Fastener engineering link added | NA | Arvind Udgi | 2025-10-20 | 2025-12-26 | Q&A | Closed | Welcome to Fastener Engineering
34 | CRIDIX Training | Icreate | Need more clarity on how to review CRIDIX | Training session / discussion | Live cridx reviewed | NA | Akash Hanwate | 2025-11-25 | 2025-12-22 | knowlege sharing | Closed
35 | Drive for Chnage | Icreate | in updated version of ICREATE, Drive for the change bucket has been changed. Does anyone has information on this new version change type, which type to be selected for Cad and Cost changes | anyone with previous experience |  |  | Anudeep Mamidi | 2025-12-03 | 2025-12-17 | Q&A | Closed
36 | Service Icrt | Icreate | need help to update procurement tab for service icrt | anyone with previous experience | In procurement Tab- Use plant need to be- Service Landrover/Jaguar | NA | Amit Saste | 2025-12-05 | 2025-10-20 | Q&A | Closed
37 | Lab test- DART | GENERAL | Lab test request | anyone has experience | DART link shared | NA | Amit Saste | 2025-12-17 | 2025-12-22 | Q&A | Closed | Durability And Reliability Testing
38 | S-dots | S-DOT | Engineering standards | anyone has experience | S-dots link shared | NA | Amit Saste | 2025-12-17 | 2025-12-22 | Q&A | Closed | http://www.sdots.jaguar.ford.com/quickstart.asp
39 | TRM-3dx | GENERAL | Engineering standards | anyone has experience | Explore in 3DX | NA | Amit Saste | 2025-12-17 | 2025-12-22 | Q&A | Closed | Explore in 3DX
40 | PCDS V4 | GENERAL | Training Session | Experienced/Expert LE's | Live Training Session | NA | Arvind Udgi | 2025-07-30 | 2025-12-31 | KSS/Training | Closed | https://jlrglobal.sharepoint.com/sites/planning-hub/SitePages/home.aspx
41 | 3DX AIMS3 | GENERAL | Training Session | Experienced/Expert LE's | Live Training Session | NA | Arvind Udgi | 2025-07-30 | 2025-12-31 | KSS/Training | Closed | https://jlrglobal.sharepoint.com/sites/3d-experience-training-online/SitePages/3DExperience-Training-AIMS2.aspx
42 | TRM(New process) 3DX | GENERAL | Training Session | Experienced/Expert LE's | Live Training Session | NA | Arvind Udgi | 2025-07-30 | 2025-12-31 | KSS/Training | Closed | https://comm.sp.jlrint.com/sites/engstd/rmdv/default.aspx
43 | Doors requirement management | GENERAL | Training Session | Experienced/Expert LE's | Live Training Session | NA | Arvind Udgi | 2025-07-30 | 2025-12-31 | KSS/Training | Closed | https://comm.sp.jlrint.com/sites/engstd/rmdv/default.aspx
44 | RMDV RTC test cases management | GENERAL | Training Session | Experienced/Expert LE's | Live Training Session | NA | Arvind Udgi | 2025-07-30 | 2025-12-31 | KSS/Training | Closed | https://comm.sp.jlrint.com/sites/engstd/rmdv/default.aspx
45 | Icreate process | GENERAL | Training Session | Experienced/Expert LE's | Live Training Session | NA | Arvind Udgi | 2025-07-30 | 2025-12-31 | KSS/Training | Closed | https://jlrglobal.sharepoint.com/sites/icreate-v2/
46 | PACN | GENERAL | Training Session | Experienced/Expert LE's | Live Training Session | NA | Arvind Udgi | 2025-07-30 | 2025-12-31 | KSS/Training | Closed | http://www.etracker.jlr.ford.com/apps/addissues/EditIssue.asp?IssueID=12738886&ProjectID=PACN
47 | Fixing Release | Icreate | Need help in raising and Icreate and releasing fixing to Ebom | anyone with previous experience | Refer IC54988 for release process 1. Release not required for fixings which are being assembled at T1(integrator) or DT2. 2. Only track fit fixing needs releasing | NA | Anudeep Mamidi | 2026-01-08 | 2026-01-09 | Q&A | Closed | https://jlrglobal.sharepoint.com/sites/3d-experience-training-online/_layouts/15/stream.aspx?id=%2Fsites%2F3d%2Dexperience%2Dtraining%2Donline%2FShared%20Documents%2FMP4%20Videos%2FP%20Release%20for%20L481and%20EMA%2FWebinars%2FCOBOT%20webinar%2Dincrease%20quantity%2C%20position%20only%2C%20add%20new%20EI%2Emp4&referrer=StreamWebApp%2EWeb&referrerScenario=AddressBarCopied%2Eview%2E99bed3f5%2De0cc%2D47b9%2D873c%2Df22a7642d9ce
48 | CA/CO & delete parts | Icreate | Whether CO/CA required for an icreate that is only for deleting parts | anyone has experience | No CO/CA required as per ERS | NA | Nivil Jose | 2026-02-11 | 2026-02-11 | Q&A | Closed
49 | CA/CO & cost collector IC | Icreate | What are the CA/O requirement for an icreate releasing only cost collectors | anyone has experience | Only USG CA required. | NA | Nivil Jose | 2026-02-11 | 2026-02-11 | Q&A | Closed
50 | 3DX UBOM | 3DX | Training Session | Experienced/Expert LE's | Training Session | NA | Sandeep Mote | 2026-01-12 | 2026-01-12 | KSS/Training | Closed | https://jlrglobal.sharepoint.com/sites/3d-experience-training-online/SitePages/Transition-to-UBOM.aspx
51 | 3DX comodity plan | 3DX | Training Session | Experienced/Expert LE's | Training Session | NA | Sandeep Mote | 2026-01-12 | 2026-01-12 | KSS/Training | Closed | https://jlrglobal.sharepoint.com/sites/3d-experience-training-online/SitePages/Training%20-%20Commodity%20Planning.aspx?csf=1&web=1&e=IH94Orhttp://
52 | 3DX EBER process | EBER | Training Session | Experienced/Expert LE's | Training Session | NA | Sandeep Mote | 2026-01-26 | 2026-01-26 | KSS/Training | Closed | https://jlrglobal.sharepoint.com/sites/3d-experience-training-online/SitePages/Training-Evidence-Based-Engineering-Review-(EBER).aspx
53 | WERS process and operating system | WERS | Training Session | Experienced/Expert LE's | Training Session | NA | Sandeep Mote | 2026-01-26 | 2026-01-26 | KSS/Training | Closed | https://jlrglobal.sharepoint.com/sites/c3png-self-help/SitePages/Worldwide-Engineering-Releasing-System-(WERS)---PROFILE.aspx
54 | WERS ALERT | WERS | Training Session | Experienced/Expert LE's | Training Session | NA | Sandeep Mote | 2026-01-26 | 2026-01-26 | KSS/Training | Closed | https://jlrglobal.sharepoint.com/sites/c3png-self-help/SitePages/Worldwide-Engineering-Releasing-System-(WERS)---ALERTS.aspx